DRAFT

Funeral Response Guide

for the

Public Information Officer

2017

# Introduction

Hello, friend,

This guide was compiled in response to funerals of five officers and one firefighter that happened between 2013 and 2017, six heartbreaking incidents of those who serve and protect being laid to rest.

Those who are left behind carry an enormous burden to honor both the dead and the living with a service paying tribute to the fallen. It seems impossible to organize something like this, especially if you are in the depths of grief, but it can be done.

You are not alone in this. Friends are here.

This guide has been produced for two reasons:

1. We want to help you plan if fate would have your agency lose one of its own in the line of duty. You need to know what to look for, what to ask for and what help is available.

2. We want you to know what to expect if you are responding as a volunteer. This guide covers what needs to happen in order for a funeral to serve its purpose and in order for the public information officer from the grieving agency to appropriately mourn.

We are great when we work together. Please remember sensitivity, tact and kindness, with some sacrifice, with accomplish great things.

With love,

The Utah PIO Association

# Table of Contents

How to request help - Contacts	Page 4

A typical timeline	Page 6

Funeral Assignments	Page 8

Position checklists

TEMPLATES

Media instructions	Page 12

News release, perpetrators ID'd	Page 15

PIO help needed email	Page 17
Talking points for the family spokesperson	Page 18

ATTACHMENTS

Venues

Shrouded badge

# How to request help - Contacts

# To start requesting PIOs

Utah PIO Association

2017-18 PIO leadership:

Roxeanne Vainuku, president

801-503-7678

roxeanne.vainuku@wvc-ut.gov

Ben Horsley, vice president

801-698-5335

bhorsley@graniteschools.org

Christina Judd, officer-at-large
801-718-9911

christina.judd@slcgov.com

Wade Mathews, past president
801-834-9741
wmathews@utah.gov

Joe Dougherty, secretary

801-538-3738
801-664-1530
jdougherty@utah.gov

# PIOs who have gone through this since 2013

Draper City
Maridene Alexander
801-831-7224

Salt Lake City Fire
Capt. Mark Bednarik
801-540-7195

Unified Police and Salt Lake County Sheriff's Office

Sgt. Cammie Skogg

801-839-9835

Chief Deputy Justin Hoyal

801-884-7024

Utah County Sheriff's Office

Sgt. Spencer Cannon
801-404-1912

Utah Highway Patrol
Sgt. Todd Royce
801-556-8261

West Valley City Police

Roxeanne Vainuku
801-503-7678

# Traffic information/collaboration

UDOT

Lisa Miller

Traveler Information Manager

Traffic Management Division

801- 887-3761

801-514-1996

lisamiller@utah.gov

Twitter: @UDOTTraffic

24/7 Traffic Operations Center – 801-887-3700

Tc-controlroom@utah.gov

# Extra American Flags

Fred Ross
Utah Transit Authority Chief of Police

801-287-2601

Email: rfredross@msn.com

Cell phone:  801-301-0552

# A typical timeline - What to expect

- Notification: This is when your department learns one of the worst fears has come to pass. Every normal thing is upset and emotions are running very high. In most cases, the incident that caused an officer’s death is over quickly. And even though an investigation is ongoing, the mourning and planning begin immediately. Consider this the start of a one-week countdown clock to a funeral. But don’t forget to be a human and mourn, as well.

- Media inquiries: These are going to come from everyone who covers your jurisdiction. Prepare to hold a press conference as soon as possible after the next of kin have been notified. It’s possible that these inquiries can come even before you are officially notified. 

This is when you will likely release official photos are record of service of the officer to the media. So gather those items now for your department.

- First contact from the PIO Association: At some point after two hours of the news being out, the PIO Association will send a PIO to you to be your personal assistant. This is someone who can help take notes, keep your phone charged and report back to PIO Association leadership with situation updates.

- After the first two days, media inquiries start to drop off, but will pick up as soon as your have a funeral date, time and location. Don’t forget that around day two or three afterward, someone will organize a candlelight vigil, likely near your agency. It may be useful to provide the officer’s car somewhere where people can leave flowers and notes of condolences. In the early stages of funeral planning, let the PIO Association gather your team, soliciting volunteers to take on a number of duties and make most of the assignments. We’ll consult with you before final assignments go out.

- Funeral planning goes into 5th Gear: This is where you are having regular meetings and reviewing everyone’s assignments. As the lead PIO for your agency, you should have regular contact with your chief and the family liaison to continue understanding the family’s wishes while also providing advice to them about how things need to work. The program should be well under way at this point and any parking placards should be provided to your PIO team. Don’t forget to coordinate with UDOT for any traffic needs.
Order food for the funeral venue. The funeral is going to be a long day.

- Media briefing: Prepare materials and Google or other shareable maps and notify the media of the funeral plans, staging at the service, availability of carrying the funeral service live, travel routes, staging at the cemetery and other important items during an in-person meeting. This information should also go out on social media and on your website.

- Day before the funeral – Viewing: You will likely need to staff the viewing, depending on the location. You can use your own staff or a volunteer PIO for that. Continue reviewing plans. Make sure there is food and water available at the funeral venue.

- Day of the funeral: This is a long day, likely the longest day. You'll need your big team in place. Have your phone charged and carry a power pack charger with you. Have a briefing with PIOs on site about 90 minutes before the service begins. The body will likely arrive a couple of hours before, depending on if there’s a viewing at that venue or not. Try to let your PIO team do their jobs so you can focus on the moment.

- Afterward: Rest and sleep. Then take time to run analytics on your social media efforts, review news clips and maintain contact with the family spokesperson or representative. Plan to hold an after-action review of the operation, even if it’s on the phone, and make sure someone takes notes so this process can be further refined the next time.

# Funeral Assignments List (Large team)

You may not need to make all of these assignments

# Planning needs in advance (See Advanced planning details)

Find out family wishes

Viewing

Venues

Cortege/Processional

Assistant PIOs
Graveside services

Social media/Website/Graphic Design

Public information plan

News media

Maps

Program

Badging

# -- Day before funeral --

Viewing division

Production unit

Photography (if needed)

Videography

Social media unit

(if needed)

Media unit

Media relations at viewing and during the day

# Funeral Assignments List - continued

Public unit

Receive gifts (All of this may be done by funeral home)

Door greeters

Programs

 -- Day of funeral --

Leadership

Lead PIO

Assistant PIO (or 2)

Family liaison or PIO who communicates with family liaison

Facility PIO

Liaison with person conducting

Funeral service division

Production unit

Photography inside

Videography inside

Photography outside

Videography outside

Social media unit

Twitter at funeral

Facebook at funeral

Media unit

Media relations at funeral

Line up spokespeople from within or other agencies

Up top or floor level

Public unit

Receive gifts

Door greeters

Ushers

Programs

Explorers

VIPs

Family unit

Family privacy protection at funeral

# Funeral Assignments List - continued

Funeral cortege division

Production unit

Photography procession

Videography procession

Social media unit

Social image sharing from procession

Graveside division

Production unit

Photography graveside

Videography graveside

Social media unit

Twitter at graveside

Facebook at graveside

Media unit

Media relations at graveside

Family unit

Mobile command unit at funeral

# Advanced planning details

# Family/Employer

Find out family wishes  -- Venue, program speakers, media interviews, etc.

Identify family spokesperson
Assign officer to the family, someone close to the family
Is there a secondary employer? Coordinate information and plans with them

# Viewing venue

Private family viewing

Public viewing

Private viewing for fellow officers and employees

# Funeral venue

Find out family wishes

Is the venue big enough? Is there enough parking?

Is there a cost?

Easy access to the facility?

Do you have maps of the facility (Seating charts and Google)

Room for media to stream the funeral live?

Transportation/parking plan

# Funeral cortege (Processional)

Route plan

Assistance from local law enforcement

Flags along route

# Graveside services

Location

Maps

Parking

Media staging
Expect the Patriot Guard Riders (motorcycles)

# PIOs

Rally PIOs to help

Give them assignment sand copies of venue planning and media planning guides

Briefing -- invites, location, instructions

# Social media/Website

Set up official hashtag

Appropriate updates to website, Twitter and Facebook

PIO help will be needed

Shrouded badge design

# Public information plan

Media releases

Maps for the public

All media and social media sources

# News media

Media advisory about funeral plans

Media advisory about media briefing

Media briefing

Media plan production

Media staging at funeral and cemetery

# Map creation

Facility seating map

Facility and graveside parking and interior (if applicable)

Funeral procession map

Viewing information and map

# Program

Speakers

Family wishes (this can seemingly take a long time)

Program design

Program printing

Delivery

A/V liaison to help with funeral program, music and PowerPoint show

# Badging

Media

Assistant PIOs

# Other related events/planning

# Candlelight vigil

- Plan for the location

- Invite family members to attend

- Secure equipment, such as audio system, lectern, etc.

- Invite mayor or other official to speak

- Take pictures

# Donations (Memorial Fund)

- Get this taken care of quickly so there's just one location for people to donate.

- Otherwise, you will be overwhelmed with people asking to create all sorts of fundraisers and GoFundMe accounts.

- You may need to assign a specific staff member to deal with this.

# After the funeral

- Coordinate the compilation of all video shot during the services

- Gather news media clips

# Anniversary and other memorial events

- The one-year, two-year anniversaries will require you to share previous information, photos and videos. So prepare ahead of time for those events.

- There is a ceremony where the fallen officer's name is placed on the Utah Fallen Officer Memorial at the Capitol.

- There is at least an annual event remembering fallen officers at the Capitol, as well.

Templates

# Logos go in header area or on letterhead

# Template: Media Instructions

Coverage of Funeral and Interment of (Fallen officer)

Public Viewing – Date and times

- Public Viewing from (time to time) at the (Location).  Reporters are allowed at the Public Viewing but cameras not allowed in the area of the casket.  (An official, such as a chief or elected official) will be available for interviews at (time) at (location).

Funeral Services – (date and time)

- The funeral service begins at (time and date), at the (location) in (city). Reporters are allowed to attend the services and carry the funeral services.

- Although cameras (still and video) will be allowed in the (location), a single location will be provided from which all photography will be done.  No flashes are to be used during the service. (Also identify if/when photography will not be allowed)

- Media representatives are asked to respect the other attendees by not moving about the (location) once the services begin.

- (An official) will be available to the media prior to the services at (time one hour before the start) at the media staging area inside the (location). Media should be in place (90 minutes before). See map for staging instructions.

- There will be a section of the parking lot set up for media trucks. Media vehicles in the (location parking lot) will not be allowed to leave until all police and fire vehicles have departed in the precession. See map for staging instructions.

- A number of public information officers will be in attendance to assist with answering questions and providing assistance to media representatives. Twitter will be used extensively. Please follow (@OfficialTwitterAccountHere).

- Funeral service attendees: please approach (location) from (this direction).

Road Closures During the Funeral

- Principal road closures go here.

- Other closures.

- Please mention what businesses, locations or areas will be impacted.

- Freeway traffic: What speed should be expected

- Onramps/offramps closed along the funeral procession route: (List them here) Traffic already on the freeway will be able to pass on the left, but access to offramps will be significantly restricted by the flow of the funeral procession

Funeral Cortege

See the attached map and please follow instructions of officers directing traffic.  The processional route is: (list the route here) Officers will direct traffic appropriately within the cemetery.

Interment at (Cemetery or mortuary name) – (Date), approximately (time).

- Interment at (Cemetery or mortuary location) (address): reporters should set up at (90 minutes beforehand). and be in place (one hour before).  The media set-up area will be located on a service road within the cemetery (dirt road immediately south of the burial plot.) (Include special instructions here) See map.

- Please be aware other funerals are taking place, but those should conclude prior to (This) service.

Road Closures & Traffic Impact During the Funeral Cortege:

- (list them here)

- Notify travelers that a large funeral procession will be traveling (in which direction)  Please notify the public that there will be a steady stream of traffic – please try to avoid this area if at all possible. (Remember to coordinate with UDOT)

Finally we ask all reporters to respect the privacy of (The officer's) family and the others in attendance by not asking for interviews with family members or (affected agency) law enforcement officers and employees.  Please realize this is a sensitive time for family, friends and co-workers. (An official) will act as spokesman for (affected agency) officers.

Links/Attachments:

(funeral location) staging inside, PDF attachment

Media staging outside:

Google Map link here

Funeral Procession route:

Google Map link here
Cemetery media staging:

Google Map link here

# # #

Contacts:

Lead PIO: contact here: Phone and email and any special instructions

Graveside PIO: contact here: Phone and email

Funeral location PIO:  contact here: Phone and email

###

# Logos go in header area or on letterhead

# Template: Media advisory - Media coordination meeting

Subject line: Media coordination meeting -- (Fallen Officer) memorial

Date

MEDIA COORDINATION MEETING

Not intended for broadcast or publication

Attention producers and editors:

(Hosting agency) is hosting a coordination meeting (When) to discuss coverage of the funeral services and procession for (fallen officer) and to answer any logistical questions you may have about coverage.

This meeting will be held

Where: (Venue, address)
When: (Date and Time)
Who will attend: Public information officers from (assisting and affected agencies)
Who is invited: Producers, editors or reporters who will help coordinate media coverage of the funeral services on Friday.

We'll explain procession routes, media staging at viewing, funeral and interment.

Again, this meeting isn't intended to be a news conference, just a coordination meeting to make sure public information officers are meeting your needs while providing the utmost respect to the family.

Contact info

# Logos go in header area or on letterhead

# Template: News release - Perpetrators arrested/identified

FOR IMMEDIATE RELEASE: (DATE)

Individuals Involved in Officer's Murder Identified

When: Date, Time

Who:

FirstName LastName, Date of birth

FirstName LastName, Date of birth

Through the investigation, the individuals involved in the incident that resulted in the murder of (fallen officer) have been identified as (FirstName Last Name and First Name LastName).

Previous jail booking photos have been attached.

Contact info for PIO

###

# Logos go in header area or on letterhead

# Template: News release - Remembrance day

(Fallen officer) Remembrance Day

DRAPER, Utah.  The 1-Year Anniversary of (Fallen officer's) death is upon us.  The (Affected agency) and (fallen officer's) family are hosting a special event on (Date, Time, Venue, Address).  A Proclamation will be read by Mayor (name) proclaiming (Date and each year on that date) thereafter as the “(Fallen officer) Remembrance Day.”

(Affected agency) and (fallen officer's) family invite community members to attend the program to honor the ultimate sacrifice (fallen officer) made a year ago.

(Fallen officer) was killed in the line of duty by (one paragraph recapping the incident)

(Fallen officer) served an honorable career in law enforcement for (how much time); he thrived on community outreach and served the community of (city) with dedication and pride. He was a model officer, son, brother, husband and father. (List those left behind)

Please join us in celebrating the life and legacy of our hometown hero, (fallen officer) The event will include a short presentation, (list other events and activities here)

~ (Fallen officer) ~

End of Watch (Date)

Contact info

# Template: PIO help needed email

To: (PIO emails)

Subject: PIO help needed: (Fallen officer) Funeral Events

Body:

Urgent -- PIOs --

The media and public swarm is slamming local PIOs in advance of (fallen officer's) funeral

.

We're asking for your assistance for two events related to the funeral: The viewing and memorial service.

"Funeral services for (fallen officer) will be held (Date and Time) at the (venue, address, city). A public viewing will be held (Date and Time and Venue)

The interment will be at (Cemetery name and address)

Contact:

You'll be working with (agency PIOs)

Hit reply to this email to let us know they have help, and text (coordinating PIO), too. (cell number)

We don't have an exact location for you to deploy to yet, but please do not automatically deploy.

This is a great opportunity to help a fellow PIO!

Email signature

# Template: Talking points for family spokesperson

These are to be used to help guide the family on how to deal with the news media.

Often, families want to say something, but also want privacy.

# Statement

(Spokesperson introduces self)

We, the family and friends of  (the fallen officer), thank you and everyone else in the public for the outpouring of love and support. This is why we feel blessed to live in this community.

(Personal statement about the deceased goes here, such as "He/she was a kind, loving person who loved police work/playing with his/her kids, etc"

(Any thoughts/feelings about what caused the death, delete if not needed)

Currently, we are working on funeral arrangements. Those will be announced publicly through (which government agency).

(Family availability) Between now and the funeral, our family asks that you respect our privacy during this time of grief.

OR

We will be available tomorrow to take a few brief questions and share some memories and photographs of (the fallen officer).

Venue Seating Charts

DAVIS CONFERENCE CENTER, LAYTON

DEE EVENTS CENTER, OGDEN

MAVERIK CENTER, WEST VALLEY CITY

SALT PALACE, SALT LAKE CITY

HUNTSMAN CENTER, UNIVERSITY OF UTAH, SALT LAKE CITY

DEE GLEN SMITH SPECTRUM, UTAH STATE UNIVERSITY, LOGAN

UCCU CENTER, UTAH VALLEY UNIVERSITY, OREM

# NOTES